## Functional Test Cases
BODY ANALYZER — Functional Test Case Report
Project: AI-Powered Body Composition Analyzer ¦ Stack: Next.js 14 · FastAPI · scikit-learn · Three.js · NextAuth.js
Test Case ID | Version | Feature | Test Case | Preconditions | Steps to Execute Test Case | Test Data | Expected Output | Actual Output | Status | Bug ID | Bug Title | Screenshot | Root Cause (Issue Description) | Resolution | Execution Date | Retest Status | Remarks
▶ AUTHENTICATION
TC_001 | V1.0 | Authentication | Login with valid Google OAuth credentials | User has active Google account; OAuth configured in .env.local | 1. Open http://localhost:3001 2. Click 'Continue with Google' 3. Authorize with valid Google account | google_user@gmail.com | User authenticated; redirected to /scan page | Error: OAuth callback failed — redirect_uri_mismatch | Fail | BUG_001 | OAuth Callback Error | SS_001.png | Redirect URI in Google Console did not match NEXTAUTH_URL | Updated Authorized redirect URI to http://localhost:3001/api/auth/callback/google | 27-04-2026 |  | Initial failure on OAuth setup
TC_001 | V1.1 | Authentication | Login with valid Google OAuth credentials | Same as V1.0 | Same steps | Same credentials | User authenticated; redirected to /scan page | User authenticated; redirected to /scan page | Pass | BUG_001 | OAuth Callback Error | SS_002.png | Fixed | Verified fix | 28-04-2026 | Pass | Retest passed
TC_002 | V1.0 | Authentication | Unauthenticated access to protected route redirects to /login | User is NOT logged in | 1. Open http://localhost:3001/dashboard directly 2. Observe redirect behaviour | No session cookie | Browser redirects to /login page | Blank white page with no redirect | Fail | BUG_002 | Missing Route Guard | SS_003.png | Next.js middleware matcher did not include /dashboard route | Added /dashboard, /insights, /analytics to middleware matcher config | 27-04-2026 |  | Route protection not enforced
TC_002 | V1.1 | Authentication | Unauthenticated access to protected route redirects to /login | Same | Same steps | Same | Browser redirects to /login page | Browser redirects to /login page immediately | Pass | BUG_002 | Missing Route Guard | SS_004.png | Fixed | Verified | 28-04-2026 | Pass | Middleware working
TC_003 | V1.0 | Authentication | Sign out clears session and redirects to /login | User is logged in with Google account | 1. Login with Google 2. Click 'Sign Out' button in header 3. Observe session state | Active session token | Session cleared; user redirected to /login | Sign out button unresponsive — no action on click | Fail | BUG_003 | Sign Out Non-Functional | SS_005.png | signOut() called without callbackUrl parameter; page did not navigate | Added callbackUrl: '/login' to signOut() call in Nav component | 27-04-2026 |  | Sign out broken
TC_003 | V1.1 | Authentication | Sign out clears session and redirects to /login | Same | Same steps | Same | Session cleared; user redirected to /login | Session cleared; user redirected to /login | Pass | BUG_003 | Sign Out Non-Functional | SS_006.png | Fixed | Verified | 28-04-2026 | Pass | Sign out working
TC_004 | V1.0 | Authentication | Google profile image loads in navigation bar | User logged in with Google account that has a profile photo | 1. Login with Google account with profile photo 2. Observe Nav bar avatar | Google account with profile photo URL | Profile photo rendered in Nav avatar circle | Broken image icon shown instead of profile photo | Fail | BUG_004 | Google Profile Image Broken | SS_007.png | next.config.mjs missing remotePatterns for googleusercontent.com domain | Added remotePatterns for **.googleusercontent.com in next.config.mjs | 28-04-2026 |  | Image domain not whitelisted in Next.js config
TC_004 | V1.1 | Authentication | Google profile image loads in navigation bar | Same | Same steps | Same credentials | Profile photo rendered in Nav avatar circle | Profile photo rendered correctly in Nav bar | Pass | BUG_004 | Google Profile Image Broken | SS_008.png | Fixed | Verified | 28-04-2026 | Pass | Image loads correctly
▶ BODY SCAN INPUT
TC_005 | V1.0 | Body Scan Input | Submit scan form with valid biometric inputs | User logged in; Python backend running on port 8000 | 1. Navigate to /scan 2. Enter Name, Age=25, Height=175cm, Weight=70kg, Gender=Male 3. Upload full-body photo 4. Click 'Run ML Body Analysis' | Height: 175, Weight: 70, Age: 25, Gender: Male | Progress bar completes; user redirected to /dashboard | Progress bar completes but dashboard shows blank spinner indefinitely | Fail | BUG_005 | Dashboard Blank After Scan | SS_009.png | Race condition: dashboard checked ScanContext before localStorage hydrated | Added isHydrated flag to ScanContext; dashboard waits for hydration before redirect | 28-04-2026 |  | State hydration race condition
TC_005 | V1.1 | Body Scan Input | Submit scan form with valid biometric inputs | Same | Same steps | Same data | Progress bar completes; user redirected to /dashboard | Progress completes; /dashboard loads with all metrics | Pass | BUG_005 | Dashboard Blank After Scan | SS_010.png | Fixed | Verified | 29-04-2026 | Pass | Full flow working
TC_006 | V1.0 | Body Scan Input | Form validation prevents submission with missing required fields | User logged in; on /scan page | 1. Leave Height field empty 2. Click 'Run ML Body Analysis' 3. Observe validation | Height: (empty), Weight: 70, Age: 25 | Validation error shown; form not submitted | Form submits with empty height; analysis runs with 0 height value | Fail | BUG_006 | Missing Field Validation | SS_011.png | No client-side required field check before triggering handleAnalyze() | Added guard checking all required fields before execution in handleAnalyze() | 28-04-2026 |  | No input validation on form submit
TC_006 | V1.1 | Body Scan Input | Form validation prevents submission with missing required fields | Same | Same steps | Same | Validation error shown; form not submitted | Toast error: 'Please fill all fields and upload an image' | Pass | BUG_006 | Missing Field Validation | SS_012.png | Fixed | Verified | 29-04-2026 | Pass | Validation working
TC_007 | V1.0 | Body Scan Input | Backend offline fallback uses formula-based analysis | Python backend NOT running; user on /scan page | 1. Ensure backend is stopped 2. Fill all fields and upload image 3. Click 'Run ML Body Analysis' | Backend: offline (port 8000 closed) | Analysis completes via formula fallback; 'Formula Mode' badge shown | Spinner runs indefinitely; no fallback triggered | Fail | BUG_007 | No Backend Fallback | SS_013.png | checkBackend() fetch failure not caught; app awaited indefinitely on network error | Added try/catch around checkBackend(); FALLBACK_STEPS used when backend unreachable | 28-04-2026 |  | No graceful degradation on backend failure
TC_007 | V1.1 | Body Scan Input | Backend offline fallback uses formula-based analysis | Same | Same steps | Same | Analysis completes via formula fallback | Analysis completes; yellow 'Formula Mode' badge shown on dashboard | Pass | BUG_007 | No Backend Fallback | SS_014.png | Fixed | Verified | 29-04-2026 | Pass | Fallback working correctly
TC_008 | V1.0 | Body Scan Input | Image upload preview displayed after file selection | User on /scan page | 1. Click image upload area 2. Select a JPG file 3. Observe upload box | File: body_photo.jpg (2 MB) | Image thumbnail preview shown inside upload box | Upload box shows filename text but no image preview | Fail | BUG_008 | No Image Preview | SS_015.png | FileReader.readAsDataURL result not assigned to preview state variable | Added setPreview(reader.result) inside FileReader onload handler | 28-04-2026 |  | Preview state not updated on file read
TC_008 | V1.1 | Body Scan Input | Image upload preview displayed after file selection | Same | Same steps | Same file | Image thumbnail preview shown inside upload box | Image thumbnail rendered correctly inside upload box | Pass | BUG_008 | No Image Preview | SS_016.png | Fixed | Verified | 29-04-2026 | Pass | Preview working
▶ DASHBOARD
TC_009 | V1.0 | Dashboard | 3D body model renders correct gender-specific GLB model | Scan completed with Gender = Female | 1. Complete scan with Gender set to Female 2. Navigate to /dashboard 3. Observe 3D model viewer | Gender: Female | Female 3D GLB model rendered in viewer | Male model displayed regardless of gender selection | Fail | BUG_009 | Wrong Gender 3D Model | SS_017.png | BodyModel3D used hardcoded '/male_body.glb' path instead of reading gender prop | Fixed path: gender==='female' loads /models/female.glb, else /models/male.glb | 29-04-2026 |  | Gender prop not used in model path selection
TC_009 | V1.1 | Dashboard | 3D body model renders correct gender-specific GLB model | Same | Same steps | Gender: Female | Female 3D GLB model rendered in viewer | Female 3D model renders correctly | Pass | BUG_009 | Wrong Gender 3D Model | SS_018.png | Fixed | Verified | 29-04-2026 | Pass | Correct model loaded for gender
TC_010 | V1.0 | Dashboard | Body fat status badge displays correct colour for each classification | Scan completed; body fat = 28% (HIGH status) | 1. Complete scan resulting in HIGH body fat 2. Check Body Fat Status card badge colour | Body fat: 28% → status: HIGH | Badge displays in orange (#f97316) for HIGH status | Badge shows green colour regardless of body fat status | Fail | BUG_010 | Wrong Status Badge Colour | SS_019.png | bfStatusColors map missing HIGH and OBESE keys; fell through to default green | Added HIGH: '#f97316' and OBESE: '#ef4444' entries to bfStatusColors map | 29-04-2026 |  | Colour map incomplete for HIGH/OBESE
TC_010 | V1.1 | Dashboard | Body fat status badge displays correct colour for each classification | Same | Same steps | Same data | Badge displays in orange for HIGH status | Badge renders in orange (#f97316) for HIGH status | Pass | BUG_010 | Wrong Status Badge Colour | SS_020.png | Fixed | Verified | 29-04-2026 | Pass | Colour coding correct
TC_011 | V1.0 | Dashboard | BMI and health score display correct computed values | Scan completed: Height=175cm, Weight=70kg, Age=25 | 1. Complete scan with above inputs 2. Observe BMI and Score values on dashboard | Height: 175cm, Weight: 70kg → expected BMI: 22.9 | BMI displays 22.9; Score between 60–80 | BMI shows 0; Score shows NaN | Fail | BUG_011 | BMI and Score Show Zero | SS_021.png | computeMetrics() received string inputs from form state; arithmetic produced NaN | Added parseFloat() conversions for height, weight, age before calling computeMetrics() | 29-04-2026 |  | Type coercion missing on form values
TC_011 | V1.1 | Dashboard | BMI and health score display correct computed values | Same | Same steps | Same data | BMI: 22.9; Score between 60–80 | BMI: 22.9, Score: 74 displayed correctly | Pass | BUG_011 | BMI and Score Show Zero | SS_022.png | Fixed | Verified | 29-04-2026 | Pass | Values computed correctly
TC_012 | V1.0 | Dashboard | Refreshing /dashboard page retains scan results | Scan completed; currently on /dashboard | 1. Complete a scan 2. View dashboard 3. Press Cmd+R to hard reload the page | Scan results stored in localStorage | Dashboard reloads and displays same scan results | Dashboard reloads then immediately redirects to /scan (results lost) | Fail | BUG_012 | Dashboard Loses Results on Refresh | SS_023.png | Redirect fired before localStorage read completed; isHydrated check missing | Added isHydrated state to ScanContext; pages wait for hydration before any redirect | 29-04-2026 |  | Premature redirect before context hydration
TC_012 | V1.1 | Dashboard | Refreshing /dashboard page retains scan results | Same | Same steps | Same | Dashboard reloads and displays same scan results | Dashboard reloads and displays previous scan results correctly | Pass | BUG_012 | Dashboard Loses Results on Refresh | SS_024.png | Fixed | Verified | 29-04-2026 | Pass | Persistence working correctly
▶ INSIGHTS
TC_013 | V1.0 | Insights | Insights page loads with personalised nutrition plan | Scan completed; navigating to /insights | 1. Complete scan 2. Navigate to /insights 3. Review Nutrition Plan section | Body fat: 22%, BMI: 24.5, Gender: Male | At least 5 personalised nutrition tips displayed | Insights page shows loading spinner and never resolves | Fail | BUG_013 | Insights Page Stuck Loading | SS_025.png | isHydrated guard missing on Insights page; attempted to read results before context loaded | Added isHydrated guard and LoadingScreen component identical to dashboard pattern | 29-04-2026 |  | Hydration guard missing on Insights page
TC_013 | V1.1 | Insights | Insights page loads with personalised nutrition plan | Same | Same steps | Same data | At least 5 personalised nutrition tips displayed | 6 nutrition recommendations displayed based on scan data | Pass | BUG_013 | Insights Page Stuck Loading | SS_026.png | Fixed | Verified | 29-04-2026 | Pass | Insights loading correctly
TC_014 | V1.0 | Insights | Exercise protocol recommendations match body fat classification | Scan completed with HIGH body fat (27%) | 1. Complete scan with HIGH body fat 2. Navigate to Insights 3. Review Exercise Protocol section | Body fat: 27% → status: HIGH | Exercise plan includes fat-burning focused recommendations | Generic exercise plan shown regardless of body fat status | Fail | BUG_014 | Exercise Plan Not Personalised | SS_027.png | Exercise plan used hardcoded default array; bfStatus not used to select appropriate plan | Added conditional plan selection in computeMetrics() based on bfStatus thresholds | 29-04-2026 |  | Exercise plan not driven by body fat status
TC_014 | V1.1 | Insights | Exercise protocol recommendations match body fat classification | Same | Same steps | Same data | Exercise plan includes fat-burning focused recommendations | Plan shows 'High-intensity cardio' and 'Caloric deficit training' for HIGH status | Pass | BUG_014 | Exercise Plan Not Personalised | SS_028.png | Fixed | Verified | 30-04-2026 | Pass | Plan personalised correctly
TC_015 | V1.0 | Insights | TDEE, BMR and hydration target computed correctly for female | Scan completed: Height=170, Weight=65, Age=30, Gender=Female | 1. Complete scan with above inputs 2. Navigate to /insights 3. Check Advanced Estimations | Height: 170, Weight: 65, Age: 30, Gender: Female | BMR ≈ 1450 kcal, TDEE ≈ 2000 kcal, Hydration ≈ 2.3L | BMR and TDEE show 0; hydration shows NaN L | Fail | BUG_015 | TDEE/BMR Zero for Female | SS_029.png | Mifflin-St Jeor female formula had sign error: -161 applied as +161 for female branch | Corrected female BMR formula to: 10*weight + 6.25*height - 5*age - 161 | 29-04-2026 |  | Wrong sign in female BMR formula
TC_015 | V1.1 | Insights | TDEE, BMR and hydration target computed correctly for female | Same | Same steps | Same data | BMR ≈ 1450 kcal, TDEE ≈ 2000 kcal, Hydration ≈ 2.3L | BMR: 1447, TDEE: 2024, Hydration: 2.3L — all values correct | Pass | BUG_015 | TDEE/BMR Zero for Female | SS_030.png | Fixed | Verified | 30-04-2026 | Pass | Female formula correct
▶ ANALYTICS
TC_016 | V1.0 | Analytics | ML training console simulates epoch logs when backend is offline | Backend NOT running; scan completed | 1. Navigate to /analytics 2. Click 'Run Deep ML Prediction Engine' 3. Observe console | Backend: offline | Simulated epoch logs animate in console; final MAE shown at completion | Console remains blank; button click produces no visible output | Fail | BUG_016 | ML Console Blank Offline | SS_031.png | useLiveTraining flag defaulted to true; offline path never triggered simulated log rendering | Set useLiveTraining=false when checkBackend() returns false; simulated logs now render | 29-04-2026 |  | Wrong training path selected when backend offline
TC_016 | V1.1 | Analytics | ML training console simulates epoch logs when backend is offline | Same | Same steps | Backend: offline | Simulated epoch logs animate; final MAE shown | Epoch logs animate correctly; MAE 1.02% shown at completion | Pass | BUG_016 | ML Console Blank Offline | SS_032.png | Fixed | Verified | 30-04-2026 | Pass | Simulation working
TC_017 | V1.0 | Analytics | Live ML training streams epoch logs from backend when online | Backend running on port 8000; scan completed | 1. Ensure backend is running 2. Navigate to /analytics 3. Click 'Run Deep ML Prediction Engine' | Backend: online | Live epoch logs stream in real-time from /train/stream SSE endpoint | Console shows simulated logs even though backend is online | Fail | BUG_017 | Live Training Not Triggered Online | SS_033.png | checkBackend() result was not used to set useLiveTraining flag after availability check | Added setUseLiveTraining(true) branch when checkBackend() returns true | 29-04-2026 |  | useLiveTraining flag not updated on backend check result
TC_017 | V1.1 | Analytics | Live ML training streams epoch logs from backend when online | Same | Same steps | Backend: online | Live epoch logs stream in real-time from backend | Real-time epoch logs stream from /train/stream; MAE printed on completion | Pass | BUG_017 | Live Training Not Triggered Online | SS_034.png | Fixed | Verified | 30-04-2026 | Pass | Live streaming working
TC_018 | V1.0 | Analytics | Organ risk indicators display correct severity for high body fat | Scan completed with body fat = 30% (OBESE status) | 1. Complete scan with body fat 30% 2. Navigate to /analytics 3. Check Organ Risk section | Body fat: 30%, BMI: 31 (OBESE) | Liver and Cardiovascular risk show 'Elevated'; Kidney shows 'Moderate' | All organ risk cards show 'Optimal' regardless of body fat value | Fail | BUG_018 | Organ Risk Hardcoded to Optimal | SS_035.png | Organ risk status was hardcoded string 'Optimal'; scan results not used in computation | Added dynamic organ risk computation in analytics page based on bodyFat and BMI thresholds | 30-04-2026 |  | Static hardcoded organ risk values
TC_018 | V1.1 | Analytics | Organ risk indicators display correct severity for high body fat | Same | Same steps | Same data | Liver: Elevated, Cardiovascular: Elevated, Kidney: Moderate | Liver: Elevated, Cardiovascular: Elevated, Kidney: Moderate — correctly computed | Pass | BUG_018 | Organ Risk Hardcoded to Optimal | SS_036.png | Fixed | Verified | 30-04-2026 | Pass | Risk computed dynamically
TC_019 | V1.0 | Analytics | Backend status indicator accurately reflects availability | On /analytics page; backend stopped | 1. Stop Python backend 2. Navigate to /analytics 3. Observe backend status badge | Backend: offline (port 8000 not listening) | Red 'Offline' badge shown in analytics header | Badge always shows green 'Online' regardless of backend state | Fail | BUG_019 | Backend Status Badge Always Online | SS_037.png | backendAvailable state initialised to true; badge rendered before availability check resolved | Initialised backendAvailable to null; added null/true/false conditional rendering | 30-04-2026 |  | Wrong initial state for availability flag
TC_019 | V1.1 | Analytics | Backend status indicator accurately reflects availability | Same | Same steps | Backend: offline | Red 'Offline' badge shown | Red 'Offline' badge displays correctly when backend is down | Pass | BUG_019 | Backend Status Badge Always Online | SS_038.png | Fixed | Verified | 30-04-2026 | Pass | Status indicator correct
▶ NAVIGATION & FLOW
TC_020 | V1.0 | Navigation & Flow | Complete app flow: Login → Scan → Dashboard → Insights → Analytics | Fresh browser session; no existing login or scan data | 1. Open http://localhost:3001 2. Login with Google 3. Complete scan 4. Navigate Dashboard → Insights → Analytics | Valid Google account; valid biometrics | All 4 pages load correctly with scan data persisted throughout | Redirected to /scan after login but /dashboard blank after analysis completes | Fail | BUG_020 | End-to-End Flow Broken | SS_039.png | Multiple upstream bugs: missing middleware, hydration race condition, signOut bug (BUG_002, BUG_005, BUG_003) | All individual bugs resolved; full flow verified after combined fixes applied | 29-04-2026 |  | Combination of multiple upstream bugs
TC_020 | V1.1 | Navigation & Flow | Complete app flow: Login → Scan → Dashboard → Insights → Analytics | Same | Same steps | Same credentials | All 4 pages load with scan data persisted throughout | Login → /scan → analysis → /dashboard → /insights → /analytics all work correctly | Pass | BUG_020 | End-to-End Flow Broken | SS_040.png | Fixed | Verified | 30-04-2026 | Pass | Full flow verified end-to-end
TC_021 | V1.0 | Navigation & Flow | Nav bar active page indicator highlights the current page | Logged in; navigating between pages | 1. Go to /dashboard → check active Nav link 2. Go to /insights → check active Nav link 3. Go to /analytics | Pages: Dashboard, Insights, Analytics | Correct Nav link highlighted on each respective page | All Nav links appear identical with no active/highlighted state | Fail | BUG_021 | Nav Active State Missing | SS_041.png | Nav component received hardcoded activePage='overview' from all pages; prop not passed correctly | Passed correct activePage prop value from each page component to Nav | 30-04-2026 |  | activePage prop hardcoded instead of being passed from parent
TC_021 | V1.1 | Navigation & Flow | Nav bar active page indicator highlights the current page | Same | Same steps | Same | Correct Nav link highlighted on each page | Active Nav link highlighted with green underline on each respective page | Pass | BUG_021 | Nav Active State Missing | SS_042.png | Fixed | Verified | 30-04-2026 | Pass | Nav indicator working
TC_022 | V1.0 | Navigation & Flow | run.sh starts both frontend and backend with a single command | Fresh environment; no prior venv or node_modules installed | 1. Open terminal in project root 2. Run: bash run.sh 3. Observe both services starting | No prior dependencies installed | Backend on :8000 and frontend on :3001 both running within 60 seconds | Frontend starts on port 3000 instead of 3001; OAuth callback fails with redirect mismatch | Fail | BUG_022 | Frontend Port Mismatch in run.sh | SS_043.png | run.sh did not explicitly set PORT=3001 before npm run dev; Next.js defaulted to 3000 | Added PORT=3001 prefix to npm run dev command in run.sh | 28-04-2026 |  | Port not forced in startup script
TC_022 | V1.1 | Navigation & Flow | run.sh starts both frontend and backend with a single command | Same | Same steps | Same | Both services on correct ports within 60 seconds | Backend on :8000 (✓) and frontend on :3001 (✓) confirmed via curl health check | Pass | BUG_022 | Frontend Port Mismatch in run.sh | SS_044.png | Fixed | Verified | 29-04-2026 | Pass | Both services start on correct ports
TEST EXECUTION SUMMARY
Total Test Cases (V1.0) | 22 | Initial Pass | 0 | Initial Fail | 22 | Bugs Raised | 22
Bugs Resolved | 22 | Retest Pass | 22 | Final Pass Rate | 100% | Final Fail Rate | 0%